## Detailed feedback
Detailed Feedback: HAFRG
|  |  | This consultation log is a living document and will be updated as additional consultations, responses, and actions occur. | [5 empty] | Last Updated: Feb 2026
Project: |  | Handling Automotive Flammable Refrigerant Gases
Training Package: |  | AUR
Website link: |  | Handling Automotive Flammable Refrigerant Gases - Training Product Development
Purpose: This section provides a list of all feedback so far, including any issues raised by stakeholders during this project, and the actions AUSMASA has taken to address this input.
Acronyms: PC – Performance Criteria, PE – Performance Evidence, KE – Knowledge Evidence, AC – Assessment Conditions, TC - Technical Committee
Date Received (DD/MM/YYY) | Stage received | Product Code | Product Title | Stakeholder/Organisation | Stakeholder Type | Title/Position | State /Jurisdiction | Method of communication | Question (if relevant) | Feedback (including issues raised) | TC and Stakeholders' Responses to Feedback.
17/12/2025 | Stage 1 – Initial Development | AUR20220 | Certificate II Automotive Air Conditioning Technology | TasTAFE | Education consultant | Teacher Assessor / Automotive Technician | Tasmania | Survey | Which automotive refrigerant gases are currently used in your workplace or by your technicians? | R134a (HFC-134a), R1234yf (HFO-1234yf), R600a (Isobutane) | Feedback under review by Technical Committee
[9 empty] | What safety training or procedures are currently in place for handling flammable or alternative refrigerants? | ARCtick refrigerant handling licence (Refrigerant Handling Licence – RHL), In-house safety induction or standard operating procedure (SOP), Formal training through a Registered Training Organisation (RTO), Manufacturer or supplier-provided training (e.g. on specific refrigerants or systems), Fire safety / fire extinguisher training, Use of personal protective equipment (PPE) specific to refrigerant handling | Feedback under review by Technical Committee
[9 empty] | Does AUR20220 adequately prepare technicians for modern (including flammable) refrigerants? | Partially | Feedback under review by Technical Committee
[9 empty] | Skills/knowledge not currently covered in the qualification? | RTOs should provide practical experience with handling and using flammable refrigerants, not just mention them in theory content | Feedback under review by Technical Committee
[9 empty] | Ratings of units for working safely with current/future refrigerant technologies | AURETU102 Recover vehicle refrigerants = Acceptable; AURETU105 Retrofit automotive air conditioning and HVAC systems = Acceptable; AURETU104 Diagnose and repair air conditioning and HVAC systems = Acceptable; AURETU001 Install air conditioning system, s = Acceptable; AURETU103 Service air conditioning and HVAC systems = Good | Feedback under review by Technical Committee
[9 empty] | Explanation for unit ratings | No response | No action required
[9 empty] | Emerging roles requiring additional HVAC training? | Yes, EV air conditioning system specific training and electric driven HVAC systems | Feedback under review by Technical Committee
[9 empty] | Additional comments or suggestions | Possibly the better option is to have a specific unit of competence for handling hydro carbon or blended refrigerants as there are more available than ever, without being licensed. | Feedback under review by Technical Committee
2025-12-16 | Stage 1 – Initial Development | AUR20220 | Certificate II Automotive Air Conditioning Technology | DCCEEW | Government |  | National | Email |  | Our main concern, as I’ve conveyed to Annie, is to ensure the importance of refrigerant identification is taught, as well as the risks of contaminated refrigerants. This could include how different refrigerants are recovered in a safe and/or environmentally friendly manner, including if they are potentially contaminated. This may include the pros/cons of different recovery and disposal techniques/equipment, and how the different types of refrigerants available impact safety and environmental risks and processes (i.e. scheduled refrigerants, A2L refrigerants and highly flammable refrigerants). Further, it’s important that students understand how contamination occurs (e.g. certain types of recovery units may end up unknowingly pumping contaminated refrigerant into a different vehicle’s uncontaminated system). | Feedback under review by Technical Committee
2025-12-08 | Stage 1 – Initial Development | AUR20220 | Certificate II Automotive Air Conditioning Technology | TAFE Queensland | Registered Training Organisations (RTOs) |  | Queensland | Interview | Open discussion about issues and concerns in industry and training products | • State-by-state refrigerant rules are a major safety risk. QLD bans flammable HC refrigerants, while other states (e.g., NSW) allow them. This creates a dangerous cross-border issue, as technicians in QLD may unknowingly service vehicles containing these gases. • Training on new refrigerant R1234YF is a major RTO cost barrier. The current requirement for practical training on this gas is unfeasible due to its low market penetration (5% of new cars) and the high cost of dedicated training equipment ($6,000). • The training package will be future-proofed by using refrigerant classes, not specific names. This avoids obsolescence as new gases emerge and allows for flexible, competency-based training. • A micron gauge (~$300) should be mandatory for all technicians. This tool is critical for proper leak testing and system diagnosis, a standard practice in commercial refrigeration that should be adopted in automotive. | Feedback under review by Technical Committee
08/12/2025 | Stage 1 – Initial Development | AUR20220 | Certificate II Automotive Air Conditioning Technology | WESTRAC | Registered Training Organisation - private | Trainer | New South Wales | Survey | Which automotive refrigerant gases are currently used in your workplace or by your technicians? | R134a (HFC-134a) | Feedback under review by Technical Committee
08/12/2025 |  |  |  | westrac | Registered Training Organisation - private | trainer | New South Wales | Survey | What safety training or procedures are currently in place for handling flammable or alternative refrigerants? | ARCtick refrigerant handling licence (Refrigerant Handling Licence – RHL), Fire safety / fire extinguisher training | Feedback under review by Technical Committee
08/12/2025 |  |  |  | westrac | Registered Training Organisation - private | trainer | New South Wales | Survey | Does AUR20220 adequately prepare technicians for modern (including flammable) refrigerants? | Partially | Feedback under review by Technical Committee
08/12/2025 |  |  |  | westrac | Registered Training Organisation - private | trainer | New South Wales | Survey | Skills/knowledge not currently covered in the qualification? | refrigerant identifcation | Feedback under review by Technical Committee
08/12/2025 |  |  |  | westrac | Registered Training Organisation - private | trainer | New South Wales | Survey | Ratings of units for working safely with current/future refrigerant technologies | AURETU103 Service air conditioning and HVAC systems = Good; AURETU104 Diagnose and repair air conditioning and HVAC systems = Good; AURETU102 Recover vehicle refrigerants = Good | Feedback under review by Technical Committee
08/12/2025 |  |  |  | westrac | Registered Training Organisation - private | trainer | New South Wales | Survey | Explanation for unit ratings | No response | No action required
08/12/2025 |  |  |  | westrac | Registered Training Organisation - private | trainer | New South Wales | Survey | Emerging roles requiring additional HVAC training? | Yes in mining HV electricains can do the training but there trade is not recognised unless they do some RPL | Feedback under review by Technical Committee
08/12/2025 |  |  |  | westrac | Registered Training Organisation - private | trainer | New South Wales | Survey | Additional comments or suggestions | as in question 6 | Feedback under review by Technical Committee
04/12/2025 | Stage 1 – Initial Development | AUR20220 | Certificate II Automotive Air Conditioning Technology | WESTRAC PTY LTD | Registered Training Organisation - private | Pre Trade Supervisor | Western Australia | Survey | Which automotive refrigerant gases are currently used in your workplace or by your technicians? | R134a (HFC-134a), R1234yf (HFO-1234yf), R290 (Propane) | Feedback under review by Technical Committee
04/12/2025 |  |  |  | WESTRAC PTY LTD | Registered Training Organisation - private | Pre Trade Supervisor | Western Australia | Survey | What safety training or procedures are currently in place for handling flammable or alternative refrigerants? | ARCtick refrigerant handling licence (Refrigerant Handling Licence – RHL), Formal training through a Registered Training Organisation (RTO) | Feedback under review by Technical Committee
04/12/2025 |  |  |  | WESTRAC PTY LTD | Registered Training Organisation - private | Pre Trade Supervisor | Western Australia | Survey | Does AUR20220 adequately prepare technicians for modern (including flammable) refrigerants? | Yes – Fully | Feedback under review by Technical Committee
04/12/2025 |  |  |  | WESTRAC PTY LTD | Registered Training Organisation - private | Pre Trade Supervisor | Western Australia | Survey | Skills/knowledge not currently covered in the qualification? | Large refrigerant capacity, battery electric HAVC systems | Feedback under review by Technical Committee
04/12/2025 |  |  |  | WESTRAC PTY LTD | Registered Training Organisation - private | Pre Trade Supervisor | Western Australia | Survey | Ratings of units for working safely with current/future refrigerant technologies | AURETU102 Recover vehicle refrigerants = Good; AURETU105 Retrofit automotive air conditioning and HVAC systems = Good; AURETU104 Diagnose and repair air conditioning and HVAC systems = Good; AURETU001 Install air conditioning systems = Acceptable; AU, RETU007 Overhaul air conditioning and HVAC system compressors = Good; AURETU103 Service air conditioning and HVAC systems = Good | Feedback under review by Technical Committee
04/12/2025 |  |  |  | WESTRAC PTY LTD | Registered Training Organisation - private | Pre Trade Supervisor | Western Australia | Survey | Explanation for unit ratings | No response | No action required
04/12/2025 |  |  |  | WESTRAC PTY LTD | Registered Training Organisation - private | Pre Trade Supervisor | Western Australia | Survey | Emerging roles requiring additional HVAC training? | Battery electric mobile plant mechanics | Feedback under review by Technical Committee
04/12/2025 |  |  |  | WESTRAC PTY LTD | Registered Training Organisation - private | Pre Trade Supervisor | Western Australia | Survey | Additional comments or suggestions | The existance of HyChil refrigerant needs to be addressed. Any unskilled individual can buy AC gauge set and HyChil and play with a refrigeration system. This causes contamination and uncertainty on what refrigerant is in s system. . | Feedback under review by Technical Committee
04/12/2025 | Stage 1 – Initial Development | AUR20220 | Certificate II Automotive Air Conditioning Technology | Westrac | Registered Training Organisation - private | Pre-Trade Training Manager | New South Wales, Western Australia | Survey | Which automotive refrigerant gases are currently used in your workplace or by your technicians? | R134a (HFC-134a), R1234yf (HFO-1234yf), Other | Feedback under review by Technical Committee
04/12/2025 |  |  |  | Westrac | Registered Training Organisation - private | Pre-Trade Training Manager | New South Wales, Western Australia | Survey | What safety training or procedures are currently in place for handling flammable or alternative refrigerants? | ARCtick refrigerant handling licence (Refrigerant Handling Licence – RHL), In-house safety induction or standard operating procedure (SOP), Manufacturer or supplier-provided training (e.g. on specific refrigerants or systems), Fire safety / fire extinguisher training, Use of personal protective equipment (PPE) specific to refrigerant handling | Feedback under review by Technical Committee
04/12/2025 |  |  |  | Westrac | Registered Training Organisation - private | Pre-Trade Training Manager | New South Wales, Western Australia | Survey | Does AUR20220 adequately prepare technicians for modern (including flammable) refrigerants? | No – Not adequately | Feedback under review by Technical Committee
04/12/2025 |  |  |  | Westrac | Registered Training Organisation - private | Pre-Trade Training Manager | New South Wales, Western Australia | Survey | Skills/knowledge not currently covered in the qualification? | refrigerant identification needs to be allot stronger, there isnt a refrigerant identified in the listed resources required. The performance evidence should be tighter around this now | Feedback under review by Technical Committee
04/12/2025 |  |  |  | Westrac | Registered Training Organisation - private | Pre-Trade Training Manager | New South Wales, Western Australia | Survey | Ratings of units for working safely with current/future refrigerant technologies | AURETU103 Service air conditioning and HVAC systems = Acceptable; AURETU007 Overhaul air conditioning and HVAC system compressors = Very Poor; AURETU001 Install air conditioning systems = Very Poor; AURETU104 Diagnose and repair air conditioning and , HVAC systems = Acceptable; AURETU105 Retrofit automotive air conditioning and HVAC systems = Very Poor; AURETU102 Recover vehicle refrigerants = Acceptable | Feedback under review by Technical Committee
04/12/2025 |  |  |  | Westrac | Registered Training Organisation - private | Pre-Trade Training Manager | New South Wales, Western Australia | Survey | Explanation for unit ratings | I rated poor the units i do not teach or wish to review as some could probably be deleted, no one overhauls compressors anymore, parts are rarely available, intstall and retrofit are the same to me, i have never done a retrofit in 20 years and i have never done an install on a blank machine. The units i rated in the middle, could do with alot of work, lots of double up in them, they should be setup as pre req style so we dont double teach, you cant do 104 until you have done 103. They need more around refrigerant ID | Feedback under review by Technical Committee
04/12/2025 |  |  |  | Westrac | Registered Training Organisation - private | Pre-Trade Training Manager | New South Wales, Western Australia | Survey | Emerging roles requiring additional HVAC training? | Not in my opinion, I think the Cert 2 is enough, and the 103 &amp; 104 units is enough for anyone with a trade | Feedback under review by Technical Committee
04/12/2025 |  |  |  | Westrac | Registered Training Organisation - private | Pre-Trade Training Manager | New South Wales, Western Australia | Survey | Additional comments or suggestions | It would be good if we could CT UEE quals into the cert 2 if they were trade based or if ARCTIC could accept a lower qual for the license as the 2 units when taught correctly are enough to ensure there is no release of refrigerant to the atmosphere | Feedback under review by Technical Committee
04/12/2025 | Stage 1 – Initial Development | AUR20220 | Certificate II Automotive Air Conditioning Technology | Motor Trades Association SA / NT | Registered Training Organisation - private | Education and Program Development Manager | South Australia | Survey | Which automotive refrigerant gases are currently used in your workplace or by your technicians? | R134a (HFC-134a), R1234yf (HFO-1234yf), Other | Feedback under review by Technical Committee
04/12/2025 |  |  |  | Motor Trades Association SA / NT | Registered Training Organisation - private | Education and Program Development Manager | South Australia |  | What safety training or procedures are currently in place for handling flammable or alternative refrigerants? | ARCtick refrigerant handling licence (Refrigerant Handling Licence – RHL), In-house safety induction or standard operating procedure (SOP), Formal training through a Registered Training Organisation (RTO), Fire safety / fire extinguisher training, Use of personal protective equipment (PPE) specific to refrigerant handling, Safe work method statements (SWMS) or risk assessments in place | Feedback under review by Technical Committee
04/12/2025 |  |  |  | Motor Trades Association SA / NT | Registered Training Organisation - private | Education and Program Development Manager | South Australia |  | Does AUR20220 adequately prepare technicians for modern (including flammable) refrigerants? | Yes – Fully | Feedback under review by Technical Committee
04/12/2025 |  |  |  | Motor Trades Association SA / NT | Registered Training Organisation - private | Education and Program Development Manager | South Australia |  | Skills/knowledge not currently covered in the qualification? | No, AURETU102 covers HC refrigerants. Manufacturers specifications and procedures explain all necessary processes and precautions. | Feedback under review by Technical Committee
04/12/2025 |  |  |  | Motor Trades Association SA / NT | Registered Training Organisation - private | Education and Program Development Manager | South Australia |  | Ratings of units for working safely with current/future refrigerant technologies | AURETU102 Recover vehicle refrigerants = Very Good; AURETU105 Retrofit automotive air conditioning and HVAC systems = Poor; AURETU104 Diagnose and repair air conditioning and HVAC systems = Very Good; AURETU001 Install air conditioning systems = Good, ; AURETU007 Overhaul air conditioning and HVAC system compressors = Good; AURETU103 Service air conditioning and HVAC systems = Very Good | Feedback under review by Technical Committee
04/12/2025 |  |  |  | Motor Trades Association SA / NT | Registered Training Organisation - private | Education and Program Development Manager | South Australia |  | Explanation for unit ratings | Retrofitting, installing and overhauling of air conditioning systems is rarely done and in some cases illegal under environmental law. Not really a relevant unit anymore. | Feedback under review by Technical Committee
04/12/2025 |  |  |  | Motor Trades Association SA / NT | Registered Training Organisation - private | Education and Program Development Manager | South Australia |  | Emerging roles requiring additional HVAC training? | Panel beating is a role that should be at the forefront of needing air conditioning training as well as those working in vehicle dismantlers. | Feedback under review by Technical Committee
04/12/2025 |  |  |  | Motor Trades Association SA / NT | Registered Training Organisation - private | Education and Program Development Manager | South Australia |  | Additional comments or suggestions | None. | No action required
04/12/2025 | Stage 1 – Initial Development | AUR20220 | Certificate II Automotive Air Conditioning Technology | Australian Refrigeration Council | Licensing and regulatory bodies | General Manager | National | Survey | Which automotive refrigerant gases are currently used in your workplace or by your technicians? | R134a (HFC-134a), R1234yf (HFO-1234yf), R744 (CO₂) | Feedback under review by Technical Committee
04/12/2025 |  |  |  | Australian Refrigeration Council | Licensing and regulatory bodies | General Manager | National | Survey | What safety training or procedures are currently in place for handling flammable or alternative refrigerants? | ARCtick refrigerant handling licence (Refrigerant Handling Licence – RHL) | Feedback under review by Technical Committee
04/12/2025 |  |  |  | Australian Refrigeration Council | Licensing and regulatory bodies | General Manager | National | Survey | Does AUR20220 adequately prepare technicians for modern (including flammable) refrigerants? | Partially | Feedback under review by Technical Committee
04/12/2025 |  |  |  | Australian Refrigeration Council | Licensing and regulatory bodies | General Manager | National | Survey | Skills/knowledge not currently covered in the qualification? | No | No action required
04/12/2025 |  |  |  | Australian Refrigeration Council | Licensing and regulatory bodies | General Manager | National | Survey | Ratings of units for working safely with current/future refrigerant technologies | AURETU102 Recover vehicle refrigerants = Acceptable; AURETU105 Retrofit automotive air conditioning and HVAC systems = Poor; AURETU104 Diagnose and repair air conditioning and HVAC systems = Acceptable; AURETU001 Install air conditioning systems = Ac, ceptable; AURETU007 Overhaul air conditioning and HVAC system compressors = Acceptable; AURETU103 Service air conditioning and HVAC systems = Acceptable | Feedback under review by Technical Committee
04/12/2025 |  |  |  | Australian Refrigeration Council | Licensing and regulatory bodies | General Manager | National | Survey | Explanation for unit ratings | Must follow what the system is designed for | Feedback under review by Technical Committee
04/12/2025 |  |  |  | Australian Refrigeration Council | Licensing and regulatory bodies | General Manager | National | Survey | Emerging roles requiring additional HVAC training? | No response | No action required
04/12/2025 |  |  |  | Australian Refrigeration Council | Licensing and regulatory bodies | General Manager | National | Survey | Additional comments or suggestions | False | No action required
04/12/2025 | Stage 1 – Initial Development | AUR20220 | Certificate II Automotive Air Conditioning Technology | South metropolitan tafe | Registered Training Organisation - public | Lecturer | Western Australia | Survey | Which automotive refrigerant gases are currently used in your workplace or by your technicians? | R134a (HFC-134a), R1234yf (HFO-1234yf) | Feedback under review by Technical Committee
04/12/2025 |  |  |  | South metropolitan tafe | Registered Training Organisation - public | Lecturer | Western Australia | Survey | What safety training or procedures are currently in place for handling flammable or alternative refrigerants? | ARCtick refrigerant handling licence (Refrigerant Handling Licence – RHL), In-house safety induction or standard operating procedure (SOP), Formal training through a Registered Training Organisation (RTO), Use of personal protective equipment (PPE) specific to refrigerant handling, Safe work method statements (SWMS) or risk assessments in place | Feedback under review by Technical Committee
04/12/2025 |  |  |  | South metropolitan tafe | Registered Training Organisation - public | Lecturer | Western Australia | Survey | Does AUR20220 adequately prepare technicians for modern (including flammable) refrigerants? | Yes – Fully | Feedback under review by Technical Committee
04/12/2025 |  |  |  | South metropolitan tafe | Registered Training Organisation - public | Lecturer | Western Australia | Survey | Skills/knowledge not currently covered in the qualification? | no | No action required
04/12/2025 |  |  |  | South metropolitan tafe | Registered Training Organisation - public | Lecturer | Western Australia | Survey | Ratings of units for working safely with current/future refrigerant technologies | AURETU102 Recover vehicle refrigerants = Very Good; AURETU105 Retrofit automotive air conditioning and HVAC systems = Very Poor; AURETU104 Diagnose and repair air conditioning and HVAC systems = Very Good; AURETU001 Install air conditioning systems =, Very Good; AURETU007 Overhaul air conditioning and HVAC system compressors = Poor; AURETU103 Service air conditioning and HVAC systems = Very Good | Feedback under review by Technical Committee
04/12/2025 |  |  |  | South metropolitan tafe | Registered Training Organisation - public | Lecturer | Western Australia | Survey | Explanation for unit ratings | Overhaul isnt really used intodays variable displacement compressors if serviced correctly. You cant retrofit from r134a to r1234yf so no need for that unit. | Feedback under review by Technical Committee
04/12/2025 |  |  |  | South metropolitan tafe | Registered Training Organisation - public | Lecturer | Western Australia | Survey | Emerging roles requiring additional HVAC training? | With upto date journals of the new refrigerant systems should be able to keep technicians knowledgable. | Feedback under review by Technical Committee
04/12/2025 |  |  |  | South metropolitan tafe | Registered Training Organisation - public | Lecturer | Western Australia | Survey | Additional comments or suggestions | I believe it should stay a licensed trade so then less failures of ac systems. | Feedback under review by Technical Committee
04/12/2025 | Stage 1 – Initial Development | AUR20220 | Certificate II Automotive Air Conditioning Technology | Victorian Automotive Chamber of Commerce | Industry Association | Executive Manager Membership &amp; Training | Tasmania, Victoria | Survey | Which automotive refrigerant gases are currently used in your workplace or by your technicians? | R134a (HFC-134a), R1234yf (HFO-1234yf), R290 (Propane), R600a (Isobutane) | Feedback under review by Technical Committee
04/12/2025 |  |  |  | Victorian Automotive Chamber of Commerce | Industry Association | Executive Manager Membership &amp; Training | Tasmania, Victoria | Survey | What safety training or procedures are currently in place for handling flammable or alternative refrigerants? | ARCtick refrigerant handling licence (Refrigerant Handling Licence – RHL), In-house safety induction or standard operating procedure (SOP), Formal training through a Registered Training Organisation (RTO), Use of personal protective equipment (PPE) specific to refrigerant handling | Feedback under review by Technical Committee
04/12/2025 |  |  |  | Victorian Automotive Chamber of Commerce | Industry Association | Executive Manager Membership &amp; Training | Tasmania, Victoria | Survey | Does AUR20220 adequately prepare technicians for modern (including flammable) refrigerants? | Yes – Fully | No action required
04/12/2025 |  |  |  | Victorian Automotive Chamber of Commerce | Industry Association | Executive Manager Membership &amp; Training | Tasmania, Victoria | Survey | Skills/knowledge not currently covered in the qualification? | Addition information surrounding R744 refrigerant | Feedback under review by Technical Committee
04/12/2025 |  |  |  | Victorian Automotive Chamber of Commerce | Industry Association | Executive Manager Membership &amp; Training | Tasmania, Victoria | Survey | Ratings of units for working safely with current/future refrigerant technologies | AURETU102 Recover vehicle refrigerants = Good; AURETU105 Retrofit automotive air conditioning and HVAC systems = Good; AURETU104 Diagnose and repair air conditioning and HVAC systems = Good; AURETU001 Install air conditioning systems = Acceptable; AU, RETU007 Overhaul air conditioning and HVAC system compressors = Acceptable; AURETU103 Service air conditioning and HVAC systems = Good | Feedback under review by Technical Committee
04/12/2025 |  |  |  | Victorian Automotive Chamber of Commerce | Industry Association | Executive Manager Membership &amp; Training | Tasmania, Victoria | Survey | Explanation for unit ratings | No response | No action required
04/12/2025 |  |  |  | Victorian Automotive Chamber of Commerce | Industry Association | Executive Manager Membership &amp; Training | Tasmania, Victoria | Survey | Emerging roles requiring additional HVAC training? | EV technicians require different modified skills and knowledge or the current units need to be flexible in providing this gap without impacting current majority of industry requirements | Feedback under review by Technical Committee
04/12/2025 |  |  |  | Victorian Automotive Chamber of Commerce | Industry Association | Executive Manager Membership &amp; Training | Tasmania, Victoria | Survey | Additional comments or suggestions | The recent changes by the Federal Government has seen further recognition of AUR qualifications across the industry that clearly would not have the skills and knowledge to work on A/C systems, this change also introduced the AUR20420 qualification | Feedback under review by Technical Committee
03/12/2025 | Stage 1 – Initial Development | AUR20220 | Certificate II Automotive Air Conditioning Technology | TAFE NSW | Registered Training Organisation - public | Automotive Airconditioning Trainer | New South Wales | Survey | Which automotive refrigerant gases are currently used in your workplace or by your technicians? | R134a (HFC-134a), R1234yf (HFO-1234yf) | Feedback under review by Technical Committee
03/12/2025 |  |  |  | TAFE NSW | Registered Training Organisation - public | Automotive Airconditioning Trainer | New South Wales | Survey | What safety training or procedures are currently in place for handling flammable or alternative refrigerants? | ARCtick refrigerant handling licence (Refrigerant Handling Licence – RHL), Formal training through a Registered Training Organisation (RTO), Manufacturer or supplier-provided training (e.g. on specific refrigerants or systems), Fire safety / fire extinguisher training, Emergency response and spill management procedures, Use of personal protective equipment (PPE) specific to refrigerant handling, Safe work method statements (SWMS) or risk assessments in place | Feedback under review by Technical Committee
03/12/2025 |  |  |  | TAFE NSW | Registered Training Organisation - public | Automotive Airconditioning Trainer | New South Wales | Survey | Does AUR20220 adequately prepare technicians for modern (including flammable) refrigerants? | No – Not adequately | Feedback under review by Technical Committee
03/12/2025 |  |  |  | TAFE NSW | Registered Training Organisation - public | Automotive Airconditioning Trainer | New South Wales | Survey | Skills/knowledge not currently covered in the qualification? | Testing of refrigerants before recovery, OEM information access, How to recover contaminated refrigerants into automatic recovery machines. | Feedback under review by Technical Committee
03/12/2025 |  |  |  | TAFE NSW | Registered Training Organisation - public | Automotive Airconditioning Trainer | New South Wales | Survey | Ratings of units for working safely with current/future refrigerant technologies | AURETU102 Recover vehicle refrigerants = Good; AURETU105 Retrofit automotive air conditioning and HVAC systems = Very Poor; AURETU104 Diagnose and repair air conditioning and HVAC systems = Good; AURETU001 Install air conditioning systems = Very Poor, ; AURETU007 Overhaul air conditioning and HVAC system compressors = Very Poor; AURETU103 Service air conditioning and HVAC systems = Good | Feedback under review by Technical Committee
03/12/2025 |  |  |  | TAFE NSW | Registered Training Organisation - public | Automotive Airconditioning Trainer | New South Wales | Survey | Explanation for unit ratings | Retrofit AC systems is a non-event - there are no systems on the market in light vehicle that require this. Overhaul compressors falls into the same boat. D&amp;R HVAC systems does not cover electric / high voltage AC compressors or Heat pump systems found in modern hybrid / Electric vehicles. | Feedback under review by Technical Committee
03/12/2025 |  |  |  | TAFE NSW | Registered Training Organisation - public | Automotive Airconditioning Trainer | New South Wales | Survey | Emerging roles requiring additional HVAC training? | EV / Hybrid technicians require skills training on Heat pump systems - and those that include HV compressors and testing thereof. | Feedback under review by Technical Committee
03/12/2025 |  |  |  | TAFE NSW | Registered Training Organisation - public | Automotive Airconditioning Trainer | New South Wales | Survey | Additional comments or suggestions | We really need to look at OEM recommendations with drop-in replacement refrigerants - these should not be used unless approved by the HVAC system manufacturer. We need to emphasise refrigerant testing before recovery - especially with automatic machines. | Feedback under review by Technical Committee
03/12/2025 | Stage 1 – Initial Development | AUR20220 | Certificate II Automotive Air Conditioning Technology | Wodonga TAFE | Registered Training Organisation - public | instructor | Victoria | Survey | Which automotive refrigerant gases are currently used in your workplace or by your technicians? | R134a (HFC-134a) | Feedback under review by Technical Committee
03/12/2025 |  |  |  | Wodonga TAFE | Registered Training Organisation - public | instructor | Victoria | Survey | What safety training or procedures are currently in place for handling flammable or alternative refrigerants? | ARCtick refrigerant handling licence (Refrigerant Handling Licence – RHL) | Feedback under review by Technical Committee
03/12/2025 |  |  |  | Wodonga TAFE | Registered Training Organisation - public | instructor | Victoria | Survey | Does AUR20220 adequately prepare technicians for modern (including flammable) refrigerants? | No – Not adequately | Feedback under review by Technical Committee
03/12/2025 |  |  |  | Wodonga TAFE | Registered Training Organisation - public | instructor | Victoria | Survey | Skills/knowledge not currently covered in the qualification? | Flammable refrigerants should be a separate AUR unit, once the AURETR103 and 104 are completed | Feedback under review by Technical Committee
03/12/2025 |  |  |  | Wodonga TAFE | Registered Training Organisation - public | instructor | Victoria | Survey | Ratings of units for working safely with current/future refrigerant technologies | AURETU104 Diagnose and repair air conditioning and HVAC systems = Poor; AURETU103 Service air conditioning and HVAC systems = Poor | Feedback under review by Technical Committee
03/12/2025 |  |  |  | Wodonga TAFE | Registered Training Organisation - public | instructor | Victoria | Survey | Explanation for unit ratings | Flammable refrigerants should be a separate AUR unit, once the AURETR103 and 104 are completed | Feedback under review by Technical Committee
03/12/2025 |  |  |  | Wodonga TAFE | Registered Training Organisation - public | instructor | Victoria | Survey | Emerging roles requiring additional HVAC training? | Flammable refrigerants should be a separate AUR unit, once the AURETR103 and 104 are completed | Feedback under review by Technical Committee
03/12/2025 |  |  |  | Wodonga TAFE | Registered Training Organisation - public | instructor | Victoria | Survey | Additional comments or suggestions | Flammable refrigerants should be a separate AUR unit, once the AURETR103 and 104 are completed | Feedback under review by Technical Committee
01/12/2025 | Stage 1 – Initial Development | AUR20220 | Certificate II Automotive Air Conditioning Technology | MTA NSW | Employer - large business (100+ employees) | Training Manager | New South Wales | Survey | Which automotive refrigerant gases are currently used in your workplace or by your technicians? | R134a (HFC-134a), R1234yf (HFO-1234yf) | Feedback under review by Technical Committee
01/12/2025 |  |  |  | MTA NSW | Employer - large business (100+ employees) | Training Manager | New South Wales | Survey | What safety training or procedures are currently in place for handling flammable or alternative refrigerants? | ARCtick refrigerant handling licence (Refrigerant Handling Licence – RHL), Formal training through a Registered Training Organisation (RTO) | Feedback under review by Technical Committee
01/12/2025 |  |  |  | MTA NSW | Employer - large business (100+ employees) | Training Manager | New South Wales | Survey | Does AUR20220 adequately prepare technicians for modern (including flammable) refrigerants? | Partially | Feedback under review by Technical Committee
01/12/2025 |  |  |  | MTA NSW | Employer - large business (100+ employees) | Training Manager | New South Wales | Survey | Skills/knowledge not currently covered in the qualification? | As long as ETU102 is part of the qual I am ok with it. A tech needs to know how to Recover the refrigerant. | Feedback under review by Technical Committee
01/12/2025 |  |  |  | MTA NSW | Employer - large business (100+ employees) | Training Manager | New South Wales | Survey | Ratings of units for working safely with current/future refrigerant technologies | AURETU102 Recover vehicle refrigerants = Good; AURETU105 Retrofit automotive air conditioning and HVAC systems = Good; AURETU104 Diagnose and repair air conditioning and HVAC systems = Good; AURETU001 Install air conditioning systems = Acceptable; AU, RETU007 Overhaul air conditioning and HVAC system compressors = Acceptable; AURETU103 Service air conditioning and HVAC systems = Good | Feedback under review by Technical Committee
01/12/2025 |  |  |  | MTA NSW | Employer - large business (100+ employees) | Training Manager | New South Wales | Survey | Explanation for unit ratings | No response | No action required
01/12/2025 |  |  |  | MTA NSW | Employer - large business (100+ employees) | Training Manager | New South Wales | Survey | Emerging roles requiring additional HVAC training? | EV is a big one as the systems rely on AC to keep the batteries temperature regulated. | Feedback under review by Technical Committee
01/12/2025 |  |  |  | MTA NSW | Employer - large business (100+ employees) | Training Manager | New South Wales | Survey | Additional comments or suggestions | Nothing | No action required
01/12/2025 | Stage 1 – Initial Development | AUR20220 | Certificate II Automotive Air Conditioning Technology | Major Training Group | Registered Training Organisation - private | Industry Trainer and Assessor | New South Wales, Queensland | Survey | Which automotive refrigerant gases are currently used in your workplace or by your technicians? | R134a (HFC-134a) | Feedback under review by Technical Committee
01/12/2025 |  |  |  | Major training group | Registered Training Organisation - private | Industry Trainer and Assessor | New South Wales, Queensland | Survey | What safety training or procedures are currently in place for handling flammable or alternative refrigerants? | ARCtick refrigerant handling licence (Refrigerant Handling Licence – RHL) | Feedback under review by Technical Committee
01/12/2025 |  |  |  | Major training group | Registered Training Organisation - private | Industry Trainer and Assessor | New South Wales, Queensland | Survey | Does AUR20220 adequately prepare technicians for modern (including flammable) refrigerants? | Partially | Feedback under review by Technical Committee
01/12/2025 |  |  |  | Major training group | Registered Training Organisation - private | Industry Trainer and Assessor | New South Wales, Queensland | Survey | Skills/knowledge not currently covered in the qualification? | No response | No action required
01/12/2025 |  |  |  | Major training group | Registered Training Organisation - private | Industry Trainer and Assessor | New South Wales, Queensland | Survey | Ratings of units for working safely with current/future refrigerant technologies | AURETU102 Recover vehicle refrigerants = Acceptable; AURETU105 Retrofit automotive air conditioning and HVAC systems = Acceptable; AURETU104 Diagnose and repair air conditioning and HVAC systems = Acceptable; AURETU001 Install air conditioning system, s = Acceptable; AURETU007 Overhaul air conditioning and HVAC system compressors = Acceptable; AURETU103 Service air conditioning and HVAC systems = Acceptable | Feedback under review by Technical Committee
01/12/2025 |  |  |  | Major training group | Registered Training Organisation - private | Industry Trainer and Assessor | New South Wales, Queensland | Survey | Explanation for unit ratings | No response | No action required
01/12/2025 |  |  |  | Major training group | Registered Training Organisation - private | Industry Trainer and Assessor | New South Wales, Queensland | Survey | Emerging roles requiring additional HVAC training? | I feel all licence holder will require some sort of updated training or awareness with new Refrigerants entering the markets as technicians are upskilling to work on EV especially as they filter into non dealer workshops | Feedback under review by Technical Committee
01/12/2025 |  |  |  | Major training group | Registered Training Organisation - private | Industry Trainer and Assessor | New South Wales, Queensland | Survey | Additional comments or suggestions | I think really we need to know what the percentages are new of vehicles entering the market with alternative refrigerants what manufactures are moving towards alternative refrigerant’s | Feedback under review by Technical Committee
01/12/2025 | Stage 1 – Initial Development | AUR20220 | Certificate II Automotive Air Conditioning Technology | My Trade Start | Registered Training Organisation - private | Head of Training and Operations | New South Wales | Survey | Which automotive refrigerant gases are currently used in your workplace or by your technicians? | R134a (HFC-134a), R1234yf (HFO-1234yf) | Feedback under review by Technical Committee
01/12/2025 |  |  |  | My Trade Start | Registered Training Organisation - private | Head of Training and Operations | New South Wales | Survey | What safety training or procedures are currently in place for handling flammable or alternative refrigerants? | ARCtick refrigerant handling licence (Refrigerant Handling Licence – RHL), In-house safety induction or standard operating procedure (SOP), Formal training through a Registered Training Organisation (RTO), Use of personal protective equipment (PPE) specific to refrigerant handling, Safe work method statements (SWMS) or risk assessments in place | Feedback under review by Technical Committee
01/12/2025 |  |  |  | My Trade Start | Registered Training Organisation - private | Head of Training and Operations | New South Wales | Survey | Does AUR20220 adequately prepare technicians for modern (including flammable) refrigerants? | Yes – Fully | Feedback under review by Technical Committee
01/12/2025 |  |  |  | My Trade Start | Registered Training Organisation - private | Head of Training and Operations | New South Wales | Survey | Skills/knowledge not currently covered in the qualification? | The mix of High Voltage A/C compressors used in the industry. | Feedback under review by Technical Committee
01/12/2025 |  |  |  | My Trade Start | Registered Training Organisation - private | Head of Training and Operations | New South Wales | Survey | Ratings of units for working safely with current/future refrigerant technologies | AURETU105 Retrofit automotive air conditioning and HVAC systems = Acceptable; AURETU102 Recover vehicle refrigerants = Good; AURETU104 Diagnose and repair air conditioning and HVAC systems = Good; AURETU001 Install air conditioning systems = Acceptab, le; AURETU007 Overhaul air conditioning and HVAC system compressors = Acceptable; AURETU103 Service air conditioning and HVAC systems = Good | Feedback under review by Technical Committee
01/12/2025 |  |  |  | My Trade Start | Registered Training Organisation - private | Head of Training and Operations | New South Wales | Survey | Explanation for unit ratings | No response | No action required
01/12/2025 |  |  |  | My Trade Start | Registered Training Organisation - private | Head of Training and Operations | New South Wales | Survey | Emerging roles requiring additional HVAC training? | Yes - EV technicians will need to be trained as they are using refrigerants to cool battery packs down | Feedback under review by Technical Committee
01/12/2025 |  |  |  | My Trade Start | Registered Training Organisation - private | Head of Training and Operations | New South Wales | Survey | Additional comments or suggestions | the practical evidence for AURETU103 using two different types of refrigerants will need to be changed as not all sectors use different gases. | Feedback under review by Technical Committee
27/11/2025 | Stage 1 – Initial Development | AUR20220 | Certificate II Automotive Air Conditioning Technology | Box Hill Institute | Registered Training Organisation - public | Curriculum Maintenance Manager | Victoria | Survey | Which automotive refrigerant gases are currently used in your workplace or by your technicians? | Not sure / unknown | No action required
27/11/2025 |  |  |  | Box Hill Institute | Registered Training Organisation - public | Curriculum Maintenance Manager | Victoria | Survey | What safety training or procedures are currently in place for handling flammable or alternative refrigerants? | ARCtick refrigerant handling licence (Refrigerant Handling Licence – RHL) | Feedback under review by Technical Committee
27/11/2025 |  |  |  | Box Hill Institute | Registered Training Organisation - public | Curriculum Maintenance Manager | Victoria | Survey | Does AUR20220 adequately prepare technicians for modern (including flammable) refrigerants? | Unsure | No action required
27/11/2025 |  |  |  | Box Hill Institute | Registered Training Organisation - public | Curriculum Maintenance Manager | Victoria | Survey | Skills/knowledge not currently covered in the qualification? | No response | No action required
27/11/2025 |  |  |  | Box Hill Institute | Registered Training Organisation - public | Curriculum Maintenance Manager | Victoria | Survey | Ratings of units for working safely with current/future refrigerant technologies | AURETU102 Recover vehicle refrigerants = Acceptable; AURETU105 Retrofit automotive air conditioning and HVAC systems = Acceptable; AURETU104 Diagnose and repair air conditioning and HVAC systems = Acceptable; AURETU001 Install air conditioning system, s = Acceptable; AURETU007 Overhaul air conditioning and HVAC system compressors = Acceptable; AURETU103 Service air conditioning and HVAC systems = Acceptable | Feedback under review by Technical Committee
27/11/2025 |  |  |  | Box Hill Institute | Registered Training Organisation - public | Curriculum Maintenance Manager | Victoria | Survey | Explanation for unit ratings | No response | No action required
27/11/2025 |  |  |  | Box Hill Institute | Registered Training Organisation - public | Curriculum Maintenance Manager | Victoria | Survey | Emerging roles requiring additional HVAC training? | No response | No action required
27/11/2025 |  |  |  | Box Hill Institute | Registered Training Organisation - public | Curriculum Maintenance Manager | Victoria | Survey | Additional comments or suggestions | No response | No action required
24/11/2025 | Stage 1 – Initial Development | AUR20220 | Certificate II Automotive Air Conditioning Technology | North Metropolitan Tafe | Registered Training Organisation - public | Lecturer | Western Australia | Survey | Which automotive refrigerant gases are currently used in your workplace or by your technicians? | R134a (HFC-134a), Other | Feedback under review by Technical Committee
24/11/2025 |  |  |  | NM Tafe | Registered Training Organisation - public | Lecturer | Western Australia | Survey | What safety training or procedures are currently in place for handling flammable or alternative refrigerants? | ARCtick refrigerant handling licence (Refrigerant Handling Licence – RHL), In-house safety induction or standard operating procedure (SOP) | Feedback under review by Technical Committee
24/11/2025 |  |  |  | NM Tafe | Registered Training Organisation - public | Lecturer | Western Australia | Survey | Does AUR20220 adequately prepare technicians for modern (including flammable) refrigerants? | Partially | Feedback under review by Technical Committee
24/11/2025 |  |  |  | NM Tafe | Registered Training Organisation - public | Lecturer | Western Australia | Survey | Skills/knowledge not currently covered in the qualification? | Awareness of gasses | Feedback under review by Technical Committee
24/11/2025 |  |  |  | NM Tafe | Registered Training Organisation - public | Lecturer | Western Australia | Survey | Ratings of units for working safely with current/future refrigerant technologies | AURETU102 Recover vehicle refrigerants = Poor; AURETU105 Retrofit automotive air conditioning and HVAC systems = Poor; AURETU104 Diagnose and repair air conditioning and HVAC systems = Poor; AURETU001 Install air conditioning systems = Poor; AURETU00, 7 Overhaul air conditioning and HVAC system compressors = Poor; AURETU103 Service air conditioning and HVAC systems = Poor | Feedback under review by Technical Committee
24/11/2025 |  |  |  | NM Tafe | Registered Training Organisation - public | Lecturer | Western Australia | Survey | Explanation for unit ratings | work places over ride training | Feedback under review by Technical Committee
24/11/2025 |  |  |  | NM Tafe | Registered Training Organisation - public | Lecturer | Western Australia | Survey | Emerging roles requiring additional HVAC training? | R744 and EV | Feedback under review by Technical Committee
24/11/2025 |  |  |  | NM Tafe | Registered Training Organisation - public | Lecturer | Western Australia | Survey | Additional comments or suggestions | No response | No action required
20/11/2025 | Stage 1 – Initial Development | AUR20220 | Certificate II Automotive Air Conditioning Technology | TAFE Queensland Cairns | Registered Training Organisation - public | Educational Team Leader | Queensland | Survey | Which automotive refrigerant gases are currently used in your workplace or by your technicians? | R134a (HFC-134a), R1234yf (HFO-1234yf) | Feedback under review by Technical Committee
20/11/2025 |  |  |  | TAFE Queensland Cairns | Registered Training Organisation - public | Educational Team Leader | Queensland | Survey | What safety training or procedures are currently in place for handling flammable or alternative refrigerants? | ARCtick refrigerant handling licence (Refrigerant Handling Licence – RHL), In-house safety induction or standard operating procedure (SOP), Formal training through a Registered Training Organisation (RTO), Emergency response and spill management procedures, Use of personal protective equipment (PPE) specific to refrigerant handling, Safe work method statements (SWMS) or risk assessments in place | Feedback under review by Technical Committee
20/11/2025 |  |  |  | TAFE Queensland Cairns | Registered Training Organisation - public | Educational Team Leader | Queensland | Survey | Does AUR20220 adequately prepare technicians for modern (including flammable) refrigerants? | Partially | Feedback under review by Technical Committee
20/11/2025 |  |  |  | TAFE Queensland Cairns | Registered Training Organisation - public | Educational Team Leader | Queensland | Survey | Skills/knowledge not currently covered in the qualification? | legislative requirements pertaining to State regulations, retro fitting at restrictive licence levels, refrigerant type analysis, refrigerant appliance use pre and post R1234yf | Feedback under review by Technical Committee
20/11/2025 |  |  |  | TAFE Queensland Cairns | Registered Training Organisation - public | Educational Team Leader | Queensland | Survey | Ratings of units for working safely with current/future refrigerant technologies | AURETU102 Recover vehicle refrigerants = Acceptable; AURETU104 Diagnose and repair air conditioning and HVAC systems = Acceptable; AURETU103 Service air conditioning and HVAC systems = Good | Feedback under review by Technical Committee
20/11/2025 |  |  |  | TAFE Queensland Cairns | Registered Training Organisation - public | Educational Team Leader | Queensland | Survey | Explanation for unit ratings | No response | No action required
20/11/2025 |  |  |  | TAFE Queensland Cairns | Registered Training Organisation - public | Educational Team Leader | Queensland | Survey | Emerging roles requiring additional HVAC training? | Conversations need to be had around the potential use of HC's and CO2 in mobile equipment, expectations of when implementations may occur, licence requirements in using those refrigerants given high flammability and extreme operating pressure. | Feedback under review by Technical Committee
20/11/2025 |  |  |  | TAFE Queensland Cairns | Registered Training Organisation - public | Educational Team Leader | Queensland | Survey | Additional comments or suggestions | No response | No action required
18/11/2025 | Stage 1 – Initial Development | AUR20220 | Certificate II Automotive Air Conditioning Technology | North Metropolitan TAFE | Registered Training Organisation - public | Advanced industry Lecturer | Western Australia | Survey | Which automotive refrigerant gases are currently used in your workplace or by your technicians? | R134a (HFC-134a), R1234yf (HFO-1234yf), Other | Feedback under review by Technical Committee
18/11/2025 |  |  |  | North Metropolitan TAFE | Registered Training Organisation - public | Advanced industry Lecturer | Western Australia | Survey | What safety training or procedures are currently in place for handling flammable or alternative refrigerants? | ARCtick refrigerant handling licence (Refrigerant Handling Licence – RHL), Formal training through a Registered Training Organisation (RTO), Fire safety / fire extinguisher training, Use of personal protective equipment (PPE) specific to refrigerant handling, Safe work method statements (SWMS) or risk assessments in place | Feedback under review by Technical Committee
18/11/2025 |  |  |  | North Metropolitan TAFE | Registered Training Organisation - public | Advanced industry Lecturer | Western Australia | Survey | Does AUR20220 adequately prepare technicians for modern (including flammable) refrigerants? | No – Not adequately | Feedback under review by Technical Committee
18/11/2025 |  |  |  | North Metropolitan TAFE | Registered Training Organisation - public | Advanced industry Lecturer | Western Australia | Survey | Skills/knowledge not currently covered in the qualification? | Safety procedures around the use of flamable refrigerants, and the different catagories of equipment avalible eg A1, A2L and A3 equipment. | Feedback under review by Technical Committee
18/11/2025 |  |  |  | North Metropolitan TAFE | Registered Training Organisation - public | Advanced industry Lecturer | Western Australia | Survey | Ratings of units for working safely with current/future refrigerant technologies | AURETU102 Recover vehicle refrigerants = Very Good; AURETU105 Retrofit automotive air conditioning and HVAC systems = Acceptable; AURETU104 Diagnose and repair air conditioning and HVAC systems = Good; AURETU001 Install air conditioning systems = Goo, d; AURETU007 Overhaul air conditioning and HVAC system compressors = Acceptable; AURETU103 Service air conditioning and HVAC systems = Very Good | Feedback under review by Technical Committee
18/11/2025 |  |  |  | North Metropolitan TAFE | Registered Training Organisation - public | Advanced industry Lecturer | Western Australia | Survey | Explanation for unit ratings | No response | No action required
18/11/2025 |  |  |  | North Metropolitan TAFE | Registered Training Organisation - public | Advanced industry Lecturer | Western Australia | Survey | Emerging roles requiring additional HVAC training? | EV technicians will be facing issues as the HVAC and cooling systems are more complex than they use to be. | Feedback under review by Technical Committee
18/11/2025 |  |  |  | North Metropolitan TAFE | Registered Training Organisation - public | Advanced industry Lecturer | Western Australia | Survey | Additional comments or suggestions | We have created a local skill set in Western Australia to upskill automotive personal who do not have the Cert II qualification but hold a Cert III Automotive Qualification, this allows them to achive the required units to gain an ARC License | Feedback under review by Technical Committee
28/10/2025 | Stage 1 – Initial Development | AUR20220 | Certificate II Automotive Air Conditioning Technology | Mud crab mechanical | Employer - small business (5-19 employees) | Owner operator | Queensland | Survey | Which automotive refrigerant gases are currently used in your workplace or by your technicians? | R134a (HFC-134a), R1234yf (HFO-1234yf) | Feedback under review by Technical Committee
28/10/2025 |  |  |  | Mud crab mechanical | Employer - small business (5-19 employees) | Owner operator | Queensland | Survey | What safety training or procedures are currently in place for handling flammable or alternative refrigerants? | ARCtick refrigerant handling licence (Refrigerant Handling Licence – RHL), In-house safety induction or standard operating procedure (SOP), Fire safety / fire extinguisher training, Emergency response and spill management procedures, Use of personal protective equipment (PPE) specific to refrigerant handling | Feedback under review by Technical Committee
28/10/2025 |  |  |  | Mud crab mechanical | Employer - small business (5-19 employees) | Owner operator | Queensland | Survey | Does AUR20220 adequately prepare technicians for modern (including flammable) refrigerants? | Partially | Feedback under review by Technical Committee
28/10/2025 |  |  |  | Mud crab mechanical | Employer - small business (5-19 employees) | Owner operator | Queensland | Survey | Skills/knowledge not currently covered in the qualification? | There is insufficient training with regards to handling, transportation and storage. | Feedback under review by Technical Committee
28/10/2025 |  |  |  | Mud crab mechanical | Employer - small business (5-19 employees) | Owner operator | Queensland | Survey | Ratings of units for working safely with current/future refrigerant technologies | AURETU102 Recover vehicle refrigerants = Acceptable; AURETU105 Retrofit automotive air conditioning and HVAC systems = Poor; AURETU104 Diagnose and repair air conditioning and HVAC systems = Poor; AURETU001 Install air conditioning systems = Poor; AU, RETU007 Overhaul air conditioning and HVAC system compressors = Good; AURETU103 Service air conditioning and HVAC systems = Poor | Feedback under review by Technical Committee
28/10/2025 |  |  |  | Mud crab mechanical | Employer - small business (5-19 employees) | Owner operator | Queensland | Survey | Explanation for unit ratings | All the training does not go over the seriousness of high pressure gas, flammability of gas and and ensuring safe work place practices | Feedback under review by Technical Committee
28/10/2025 |  |  |  | Mud crab mechanical | Employer - small business (5-19 employees) | Owner operator | Queensland | Survey | Emerging roles requiring additional HVAC training? | Yes, the added higher voltage used by some manufacturers makes things more complicated | Feedback under review by Technical Committee
28/10/2025 |  |  |  | Mud crab mechanical | Employer - small business (5-19 employees) | Owner operator | Queensland | Survey | Additional comments or suggestions | Someone trained on a vehicle ev with split system airconditioning is really working on a house air conditioning unit on wheels | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU105 | Retrofit automotive air conditioning and HVAC system | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Performance Criteria Changes Element 1.3 Current wording: "Identify refrigerant required according to workplace procedures and workplace health and safety and environmental requirements" Recommended changes: "Identify refrigerant required according to relevant regulations, standards, workplace procedures and workplace health and safety and environmental requirements" Change: Added reference to "relevant regulations, standards" | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU105 | Retrofit automotive air conditioning and HVAC system | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Element 1.6 Current wording: "Identify tools and equipment required for inspect and servicing activity and establish serviceability according to workplace procedures" Recommended changes: "Identify tools and equipment required for the inspection and servicing activity and establish serviceability according to workplace procedures" Change: Corrected "inspect" to "the inspection" (grammar fix) | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU105 | Retrofit automotive air conditioning and HVAC system | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Element 3.1 Current: "Carry out air conditioning retrofit procedures according to manufacturer specifications, Australian automotive code of practice, workplace procedures, and workplace health safety and environmental requirements" Recommended changes: "Carry out air conditioning retrofit procedures according to relevant regulations, standards, manufacturer specifications, Australian automotive code of practice, workplace procedures, and workplace health safety and environmental requirements" Change: Added "relevant regulations, standards" | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU105 | Retrofit automotive air conditioning and HVAC system | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Performance Evidence current wording: "retrofit the air conditioning and HVAC systems of two different vehicles or machinery, in which the work must include changing the type of refrigerant." Recommended: "retrofit the air conditioning and HVAC systems of two different vehicles or machinery, in which the work must include changing the type of refrigerant. The replacement refrigerant can not: - be a more flammable or more toxic class of refrigerant than the existing refrigerant, - have a higher Global Warming Potential than the existing refrigerant." Change: Added two safety constraints about refrigerant replacement characteristics | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU105 | Retrofit automotive air conditioning and HVAC system | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Knowledge Evidence - Current wording: "procedures for changing system refrigerant, including: - changing refrigerant gas from R12 to R134a: -receiver dryer filter replacement - change system fittings for manifold gauge attachment change oil type - reasons why R134a refrigerant must not be retrofitted to R1234yf - reasons why R134a refrigerant must not be retrofitted to blends of hydrocarbons" Recommended changes: "procedures for changing system refrigerant, including: - changing refrigerant gas from R12 to R134a and/or changing R134a to drop-in replacement refrigerants (e.g. R456A, R513A) - receiver dryer filter replacement - change system fittings for manifold gauge attachment - change oil type - reasons why R134a refrigerant must not be retrofitted to R1234yf - reasons why R134a refrigerant must not be retrofitted to blends of hydrocarbons" Change: Expanded scope to include drop-in replacement refrigerants (R456A, R513A) and flattened bullet structure | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU105 | Retrofit automotive air conditioning and HVAC system | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Assessment Conditions - Current wording: "dry nitrogen cylinder and gauge" Recommended changes: "oxygen free dry nitrogen cylinder and gauge" Change: Added "oxygen free" specification for safety/quality | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU104 | Diagnose and repair air conditioning and HVAC systems | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Performance Criteria - Element 3.3 Current wording: "Connect recovery equipment to vehicle according to manufacturer specifications, workplace procedures, workplace health and safety and environmental requirements" Recommended changes: "Connect recovery equipment to vehicle according to manufacturer specifications, workplace procedures, code of practice, workplace health and safety and environmental requirements" Change: Added "code of practice" to the compliance requirements | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU104 | Diagnose and repair air conditioning and HVAC systems | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Performance Criteria - Element 3.4 Current wording: "Recover refrigerant and transfer into designated recovery cylinder using recovery equipment according to manufacturer specifications, workplace procedures, and workplace health safety and environmental requirements" Recommended changes: "Recover refrigerant and transfer into designated recovery cylinder using recovery equipment according to manufacturer specifications, workplace procedures, code of practice, workplace health safety and environmental requirements" Change: Added "code of practice" to the compliance requirements | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU104 | Diagnose and repair air conditioning and HVAC systems | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Performance Criteria - Element 4.3 Current wording: "Carry out repairs according to workplace and manufacturer procedures, manufacturer specifications, workplace health and safety and environmental requirements" Recommended changes: "Carry out repairs according to workplace and manufacturer procedures, code of practice, manufacturer specifications, workplace health and safety and environmental requirements" Change: Added "code of practice" to the compliance requirements | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU104 | Diagnose and repair air conditioning and HVAC systems | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Performance Criteria - Element 4.4 Current wording: "Recharge system with required refrigerant gas according to manufacturer specifications, workplace procedures and workplace health and safety and environmental requirements" Recommended changes: "Recharge system with required refrigerant gas according to manufacturer specifications, workplace procedures, code of practice workplace health and safety and environmental requirements" Change: Added "code of practice" to the compliance requirements | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU104 | Diagnose and repair air conditioning and HVAC systems | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Performance Criteria - Element 4.5 Current wording: "Carry out post-repair testing according to workplace procedures, workplace health and safety and environmental requirements" Recommended changes: "Carry out post-repair testing according to workplace procedures, code of practice, workplace health and safety and environmental requirements" Change: Added "code of practice" to the compliance requirements | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU104 | Diagnose and repair air conditioning and HVAC systems | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Performance Evidence - Current wording: "diagnose and repair a fault in the air conditioning and heating, ventilation and cooling (HVAC) systems of two different vehicles or machinery, in which the work must involve removing, refitting or replacing two of the following: - condenser - evaporator - expansion valve - compressor - heater box" Recommended changes: "diagnose and repair a fault in the air conditioning and heating, ventilation and cooling (HVAC) systems of two different vehicles or machinery, in which the work must involve removing, refitting or replacing two of the following: - condenser - evaporator - expansion valve - compressor - heater box - refrigerant hose" Change: Added "refrigerant hose" as a sixth component option | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU104 | Diagnose and repair air conditioning and HVAC systems | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Performance Evidence - Current wording: "remove, refit or replace two different types of refrigerant." Recommended changes: "remove, refit or replace components from systems using .a Class A1 non-flammable, non-toxic refrigerant (e.g. R134a) and an A2/A2L lower flammability, non-toxic refrigerant (e.g. R1234yf)" Change: Replaced generic "two different types of refrigerant" with specific refrigerant classification requirements (Class A1 and A2/A2L) with examples | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU104 | Diagnose and repair air conditioning and HVAC systems | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Knowledge Evidence - Current wording: "handling, storing and transporting refrigerant cylinders and recovery cylinders, including: Recommended changes: "handling, storing and transporting Class A1 and A2/A2L refrigerant cylinders and recovery cylinders, including: Change: Added "Class A1 and A2/A2L" specification to refrigerant cylinder types | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU104 | Diagnose and repair air conditioning and HVAC systems | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Knowledge Evidence - Current wording: "procedures for recovering automotive refrigerant, including:" Recommended changes: "procedures for recovering automotive Class A1 and A2/A2L refrigerant, including:" Change: Added "Class A1 and A2/A2L" specification to automotive refrigerant recovery procedures | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU104 | Diagnose and repair air conditioning and HVAC systems | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Knowledge Evidence - Current wording: "system performance testing, including: using manifold gauges and thermometers to check system pressures and vent temperatures - checking blower fan output - checking engine fan output - checking filters" Recommended changes: "system performance testing, including: using manifold gauges and thermometers to check system pressures and vent temperatures - checking blower fan output - checking engine fan output - checking filters - checking system operating pressures" Change: Added "checking system operating pressures" as an additional testing requirement | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU104 | Diagnose and repair air conditioning and HVAC systems | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Knowledge Evidence - Current wording: "repair procedures for air conditioning and HVAC systems, including procedures for: - using manifold gauges to discharge, evacuate and charge system refrigerants - removing and replacing system components" Recommended changes: "repair procedures for air conditioning and HVAC systems, including procedures for: - using manifold gauges to recover, evacuate and charge system refrigerants - removing and replacing system components" Change: Changed "discharge" to "recover" for refrigerant handling terminology | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU104 | Diagnose and repair air conditioning and HVAC systems | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Knowledge Evidence Recommended changes: NEW SECTION Added at the end "Hydrocarbon refrigerants - Flammability and sources of ignition - Constraints on their use: - State/Territory Regulations - Heads of Workplace Safety Authorities (HWSA) - Flammable refrigerant gases – position paper - Manufacturer's specifications and warranty conditions - AIRAH - Flammable refrigerant safety guide - VASA = Flammable refrigerants and safety in automotive applications" Change: Added entirely new knowledge section covering hydrocarbon refrigerants, flammability, sources of ignition, and regulatory/safety constraints, including five specific reference documents | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU104 | Diagnose and repair air conditioning and HVAC systems | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Assessment Conditions - Current wording: "minimum of two different types of refrigerant" Recommended changes: "minimum of two different types of refrigerant, that is one Class A1 and one Class A2/A2L" Change: Specified that the two refrigerant types must be one Class A1 and one Class A2/A2L | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU104 | Diagnose and repair air conditioning and HVAC systems | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Assessment Conditions - Current wording: "diagnosis and repair equipment for air conditioning and HVAC systems, including: manifold and gauge set, recovery unit, vacuum pump, electronic leak detector, nitrogen cylinder and regulator, multimeter, electronic scales, oil injector, infra-red thermometer, temperature probe, scan tool." Recommended changes: "diagnosis and repair equipment for air conditioning and HVAC systems, including: manifold and gauge set, recovery unit, vacuum pump, electronic vacuum gauge, electronic leak detector, oxygen free nitrogen cylinder and regulator, multimeter, electronic scales, oil injector, infra-red thermometer, temperature probe scan tool." Change: Added "electronic vacuum gauge" as new equipment; changed "nitrogen cylinder and regulator" to "oxygen free nitrogen cylinder and regulator" | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU103 | Service air conditioning and HVAC systems | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Knowledge Evidence - current wording: "system performance testing, including: checking blower fan output, checking engine fan output, checking filters" Recommended: "system performance testing, including: checking blower fan output, checking engine fan output, checking air filters, checking system pressures (per Performance Evidence)" Change: Changed "checking filters" to "checking air filters" for clarity; added "checking system pressures (per Performance Evidence)" as additional testing requirement | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU103 | Service air conditioning and HVAC systems | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Knowledge Evidence - Current wording: "service and adjustment procedures of air conditioning and HVAC systems, including: checking and adjusting compressor drive belts, changing filters, clearing evaporator water outlet, cleaning condenser" Recommended changes: "service and adjustment procedures of air conditioning and HVAC systems, including: checking and adjusting compressor drive belts, changing air filters, clearing evaporator condensate water outlet, cleaning condenser" Change: Changed "changing filters" to "changing air filters" for consistency; changed "clearing evaporator water outlet" to "clearing evaporator condensate water outlet" for technical accuracy | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU102 | Recover vehicle refrigerants | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Performance Criteria - Element 2.3 Current wording: "Connect recovery equipment to vehicle according to manufacturer specifications, workplace procedures, workplace health and safety and environmental requirements" Recommended changes: "Connect recovery equipment to vehicle according to manufacturer specifications, Australian automotive code of practice, workplace procedures, workplace health and safety and environmental requirements" Change: Added "Australian automotive code of practice" to compliance requirements | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU102 | Recover vehicle refrigerants | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Performance Criteria - Element 2.4 Current wording: "Recover refrigerant and transfer into designated recovery cylinder using recovery equipment according to manufacturer specifications, workplace procedures, and workplace health safety and environmental requirements" Recommended changes: "Recover refrigerant and transfer into designated recovery cylinder using recovery equipment according to manufacturer specifications, Australian automotive code of practice, workplace procedures, and workplace health safety and environmental requirements" Change: Added "Australian automotive code of practice" to compliance requirements | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU102 | Recover vehicle refrigerants | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Performance Evidence - Refrigerant types requirement current wording: "recover and identify vehicle refrigerants from three different vehicles or machinery, in which the work must involve one of the following refrigerant types: synthetic greenhouse and ozone depleting (SGOD) refrigerant, hydrocarbon (HC) refrigerant, hydrofluorocarbon (HFC) refrigerant, a mixture of SGOD and HC refrigerant." Recommended: "recover and identify vehicle refrigerants from three different vehicles or machinery, in which the work must involve both of the following refrigerant types: Class A1 non-flammable, non toxic refrigerant (e.g. R134a), Class A2/A2L low-flammability, non toxic refrigerant (e.g. R1234yf)" Change: Replaced list of four optional refrigerant types with requirement for both Class A1 and Class A2/A2L refrigerants; changed from "one of the following" to "both of the following" | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU102 | Recover vehicle refrigerants | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Performance Evidence - Current wording: "In the course of the above work, the candidate must use the following equipment: refrigerant hose and coupler, refrigerant recovery unit, refrigerant scales, refrigerant identifier or analyser, designated and appropriately labelled recovery cylinders." Recommended changes: "In the course of the above work, the candidate must use the following equipment: refrigerant hose and coupler, refrigerant recovery unit, refrigerant leak detector, refrigerant scales, refrigerant identifier or analyser, designated and appropriately labelled recovery cylinders." Change: Added "refrigerant leak detector" to required equipment list | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU102 | Recover vehicle refrigerants | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Knowledge Evidence - current wording: "key features of various types of refrigerants and oils found in automotive vehicle and equipment HVAC systems, including: synthetic SGOD refrigerants, such as: chlorofluorocarbons (CFC), hydrofluorocarbons (HFC), HC refrigerants, mineral and synthetic refrigerant oils" Recommended: "key features of various types of refrigerants and oils found in automotive vehicle and equipment HVAC systems, including: synthetic SGOD refrigerants, such as: chlorofluorocarbons (CFC), hydrofluorocarbons (HFC), Class A1 non-flammable, non toxic refrigerant (e.g. R134a), Class A2/A2L low-flammability, non toxic refrigerant (e.g. R1234yf), HC refrigerants (Class A3 flammable, non toxic refrigerant e.g. R600), mineral and synthetic refrigerant oils" Change: Added three specific refrigerant classifications with examples: "Class A1 non-flammable, non toxic refrigerant (e.g. R134a)", "Class A2/A2L low-flammability, non toxic refrigerant (e.g. R1234yf)", and expanded HC refrigerants to "HC refrigerants (Class A3 flammable, non toxic refrigerant e.g. R600)" | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU102 | Recover vehicle refrigerants | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Knowledge Evidence - Current wording: "key features of refrigerant recovery equipment, including: manifold and gauge set, recovery unit, types of recovery cylinders, refrigerant analyser, vacuum recovery equipment and scales" Recommended changes: "key features of refrigerant recovery equipment, including: manifold and gauge set, recovery unit, types of recovery cylinders, refrigerant analyser, recovery equipment and scales" Change: Removed "vacuum" before "recovery equipment and scales" (changed from "vacuum recovery equipment and scales" to "recovery equipment and scales") | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU007 | Overhaul air conditioning and HVAC system compressors | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Performance Evidence - Current wording: "overhaul the air conditioning compressors of two different vehicles or machinery, including: piston, scroll and rotary vane compressors, electric compressors, variable displacement compressors, clutchless compressors, recover and evacuate refrigerants according to required code of practice and regulations, and recharge the system with the appropriate manufacturer refrigerant and oil type." Recommended changes: "overhaul the air conditioning compressors of two different vehicles or machinery, including: piston, scroll and rotary vane compressors, electric compressors, variable displacement compressors, clutchless compressors" Change: Removed entire requirement "recover and evacuate refrigerants according to required code of practice and regulations, and recharge the system with the appropriate manufacturer refrigerant and oil type" from Performance Evidence - Note: "This does not align with the Elements and Performance Criteria which assume the compressor has already been removed from the system." | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU001 | Install air conditioning systems | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Performance Criteria - Element 2.1 Current wording: "Air conditioning system components are installed according to workplace procedures and safety and environmental requirements, and without causing damage to components and vehicle or machinery systems" Recommended changes: "Air conditioning system components are installed according to manufacturer's instructions, Australian automotive code of practice, workplace procedures and safety and environmental requirements, and without causing damage to components and vehicle or machinery systems" Change: Added "manufacturer's instructions, Australian automotive code of practice" to compliance requirements | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU001 | Install air conditioning systems | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Performance Criteria - Element 3.1 Current wording: "System is pressure tested for leaks prior to being evacuated using approved methods and equipment" Recommended changes: "System is pressure tested for leaks using oxygen free nitrogen prior to being evacuated using approved methods and equipment according to manufacturer's instructions, Australian automotive code of practice," Change: Added "using oxygen free nitrogen" and "according to manufacturer's instructions, Australian automotive code of practice" to the pressure testing requirements | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU001 | Install air conditioning systems | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Performance Criteria - Element 3.2 Current wording: "System is charged with appropriate refrigerant gas and lubricating oil according to manufacturer specifications, workplace procedures, and relevant industry code of practice" Recommended changes: "System is charged with appropriate refrigerant gas and lubricating oil according to manufacturer specifications, Australian automotive code of practice, workplace procedures, and relevant industry code of practice" Change: Added "Australian automotive code of practice" to compliance requirements | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU001 | Install air conditioning systems | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Installation Options - Current gases include: R134a R1234yf Recommended changes: R134a R1234yf R290 and R600a blends Change: Added "R290 and R600a blends" to the list of refrigerant types | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU001 | Install air conditioning systems | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Knowledge Evidence - Current wording: "requirements of Ozone Protection and Synthetic Greenhouse Gas Management Regulations 1995 during installation of motor vehicle air conditioners" Recommended changes: "requirements of Automotive code of practice: Control of refrigerant gases during manufacture, installation, servicing or de-commissioning of motor vehicle air conditioners" Change: Replaced reference to "Ozone Protection and Synthetic Greenhouse Gas Management Regulations 1995" with "Automotive code of practice: Control of refrigerant gases during manufacture, installation, servicing or de-commissioning of motor vehicle air conditioners" | Feedback under review by Technical Committee
2025-12-23 | Stage 1 – Initial Development | AURETU001 | Install air conditioning systems | Australian Refrigeration Council (ARC) | Regulator |  | National | Email |  | Tools and Equipment - Current wording: nitrogen cylinder and regulator Recommended changes: nitrogen cylinder and regulator (Assessment Conditions) oxygen free nitrogen (specified in Performance Criteria Element 3.1) Change: While the assessment conditions list remains "nitrogen cylinder and regulator," the performance criteria now specifies "oxygen free nitrogen" for pressure testing | Feedback under review by Technical Committee
| Stage 1 – Initial Development | AUR20220 | Certificate II Automotive Air Conditioning Technology | Department of Climate Change, Energy, the Environment and Water | Regulator | Assistant Director, Ozone Regulatory Maturity | National | Email |  | The main concern I would raise is to ensure the importance of refrigerant identification is taught, so any refrigerant contamination can be identified, which would impact how that refrigerant is recovered in a safe and/or environmentally friendly manner. This may include the pros/cons of different recovery and disposal techniques/equipment, and how the different types of refrigerants available impact safety and environmental risks and processes (i.e. scheduled refrigerants, A2L refrigerants and highly flammable refrigerants). | Feedback under review by Technical Committee